City of Sebastopol Engineering Department CIP Projects Update

12/2/2025

- SR 116 Enhanced Crossings at Burnett, Keating, Hutchins and Walker. This project is the removal of in-roadway warning lights and replacement with new pedestrian-activated flashing beacons replacing the existing at the four locations on SR 116. The project is currently being designed by W- Trans and anticipated to be ready for construction in early 2026.

- Bodega Avenue Bike Lanes and Pavement Rehabilitation Phase 2. This project is the installation of bike lanes and rehabilitation of the pavement on Bodega Avenue from Nelson Way to Pleasant Hill Road and additional paving between Valley View Drive and the city limit at Atascadero Creek. The project was awarded to Team Ghilotti on November 18, 2025. The work will start in January 2026, weather permitting.

- Americorps Trail Extension Project. The project is located in the Laguan Wetlands Preserve trails system from the Sebastopol Lift Station at Morris Street to Sebastopol Road (S.R. 12). The trail will include a pedestrian bridge at Zimpher Creek. The work is completed.

- Calder Creek Storm Drain at Ives Park. The project consists of a trenchless repair of a 60-inch corrugated metal storm drain pipe. The repair work is completed.

- Citywide Pavement Repairs and Repaving Program: Digouts and Repairs. The project is part of the annual street repair and repaving program in accordance with the City’s Pavement Management Program. This 2025-26 project will focus on digouts and repairs of damaged streets that requires more than pothole repairs, but less than full street reconstruction and repavement. A list of the proposed streets sis being prepared by Public Works staff and will be presented to Council for consideration at a future Council meeting in early 2026.

- Water System Master Plan Update. The City’s water master plan was last prepared in 2005 and needs updating in order to provide a comprehensive list of improvements for the Capital Improvement Program (CIP).  A draft list of capital projects will be presented to City Council in a meeting in December 2025. The City’s consultant, GHD Inc., is preparing the update and work is currently underway. The Draft report is estimated to be completed in February 2026 where it will be presented to Council for review and approval.

- Flood Resiliency Master Plan. The City has never prepared a flood resiliency or storm drainage system master plan. The master plan will include GIS asset management for the storm drainage system, citywide hot spot flooding analysis, Calder Creek area flooding analysis and a report that include recommended storm drainage improvements. The plan is being prepared by the City’s consultant, Wood Rodgers. The work is just starting and the plan is estimated to be completed at the end of 2026.

- Well 4 Replacement Project. Request for Proposals for the design and redevelopment of the City’s Well 4 (groundwater well) was released in November. Proposals are due in December 2025.

- Sewer System Master Plan Update. The City’s sewer master plan was last prepared in 2005 and needs updating in order to provide a comprehensive list of improvements for the Capital Improvement Program (CIP). A Request for Proposal (RFP) for the preparation of the master plan update will be scheduled to be released in December 2025.